## Overview
Metric | Value
Plan start | 2025-01-01
Plan end | 2026-03-31
Modules (wf_tool) | 110
Operation tasks (non-dummy) | 440
Total workload_days | 23350
Median workload_days (per op task) | 33.5
Avg workload_days (per op task) | 53.0682
Median duration_days (per op task) | 15
Avg intensity (workload/duration) | 2.9145

## Operation Summary
operation | task_count | avg_workload_days | median_workload_days | min_workload_days | max_workload_days | avg_duration_days | median_duration_days | avg_intensity | median_intensity
p1 | 110 | 68.609 | 51.5 | 1 | 326 | 18.318 | 16 | 3.507 | 3.247
p2 | 110 | 67.055 | 50.5 | 1 | 249 | 19.091 | 17 | 3.579 | 3.264
p3 | 110 | 35.1 | 28.5 | 1 | 157 | 14.536 | 12.5 | 2.663 | 2
p4 | 110 | 41.509 | 25 | 1 | 683 | 21.227 | 17 | 1.909 | 1.684

## Phase Summary
phase_id | phase_name | task_count | avg_workload_days | median_workload_days | avg_duration_days | median_duration_days | avg_intensity | median_intensity
tool_p1 | Module Setup | 110 | 68.609 | 51.5 | 18.318 | 16 | 3.507 | 3.247
tool_p2 | Hardware Setup | 110 | 67.055 | 50.5 | 19.091 | 17 | 3.579 | 3.264
tool_p3 | Function Setup | 110 | 35.1 | 28.5 | 14.536 | 12.5 | 2.663 | 2
tool_p4 | Utility | 110 | 41.509 | 25 | 21.227 | 17 | 1.909 | 1.684

## Module Summary
module_id | module_name | fab | operation_task_count | phase_count | module_start | module_end | module_duration_days | total_workload_days | avg_workload_days_per_calendar_day
e1 | 530900102A | f1 | 4 | 4 | 2025-10-14 | 2026-01-30 | 109 | 397 | 3.642
e10 | 530N02566A | f8 | 4 | 4 | 2026-01-21 | 2026-03-31 | 70 | 134 | 1.914
e100 | 830400228A | f23 | 4 | 4 | 2026-01-04 | 2026-01-17 | 14 | 14 | 1
e101 | 830400232A | f23 | 4 | 4 | 2025-09-16 | 2025-12-08 | 84 | 105 | 1.25
e102 | 830C00003A | f10 | 4 | 4 | 2025-03-02 | 2025-07-30 | 151 | 359 | 2.377
e103 | 830C00004A | f10 | 4 | 4 | 2025-01-05 | 2025-06-02 | 149 | 375 | 2.517
e104 | 830C00011A | f38 | 4 | 4 | 2026-03-16 | 2026-03-31 | 16 | 80 | 5
e105 | 830D00008A | f39 | 4 | 4 | 2025-01-06 | 2025-02-09 | 35 | 70 | 2
e106 | 830D00009A | f32 | 4 | 4 | 2025-01-08 | 2025-02-07 | 31 | 57 | 1.839
e107 | 830D00010A | f39 | 4 | 4 | 2025-01-09 | 2025-03-31 | 82 | 110 | 1.341
e108 | 840400019A | f40 | 4 | 4 | 2025-05-12 | 2025-05-16 | 5 | 21 | 4.2
e109 | 840500001A | f6 | 4 | 4 | 2025-01-01 | 2025-03-27 | 86 | 335 | 3.895
e11 | 530N02609A | f9 | 4 | 4 | 2025-01-01 | 2025-01-24 | 24 | 47 | 1.958
e110 | 840700002A | f41 | 4 | 4 | 2025-08-27 | 2026-01-23 | 150 | 587 | 3.913
e12 | 530N02615A | f3 | 4 | 4 | 2025-01-08 | 2025-02-13 | 37 | 175 | 4.73
e13 | 530N02616A | f3 | 4 | 4 | 2025-01-31 | 2025-03-10 | 39 | 35 | 0.897
e14 | 530N02620A | f3 | 4 | 4 | 2025-02-20 | 2025-03-21 | 30 | 66 | 2.2
e15 | 530N02622A | f10 | 4 | 4 | 2025-02-09 | 2025-07-23 | 165 | 290 | 1.758
e16 | 530N02623A | f10 | 4 | 4 | 2025-01-31 | 2025-06-29 | 150 | 1042 | 6.947
e17 | 530N02624A | f10 | 4 | 4 | 2025-03-04 | 2025-08-11 | 161 | 250 | 1.553
e18 | 530N02626A | f11 | 4 | 4 | 2025-01-01 | 2025-03-04 | 63 | 108 | 1.714
e19 | 530N02628A | f11 | 4 | 4 | 2025-01-01 | 2025-04-01 | 91 | 316 | 3.473
e2 | 530900112A | f2 | 4 | 4 | 2025-11-05 | 2026-01-16 | 73 | 346 | 4.74
e20 | 530N02632A | f12 | 4 | 4 | 2025-04-02 | 2025-04-06 | 5 | 5 | 1
e21 | 530N02635A | f3 | 4 | 4 | 2025-05-07 | 2025-07-24 | 79 | 288 | 3.646
e22 | 530N02639A | f6 | 4 | 4 | 2025-01-23 | 2025-03-10 | 47 | 249 | 5.298
e23 | 530N02646A | f13 | 4 | 4 | 2025-01-01 | 2025-01-18 | 18 | 18 | 1
e24 | 530N02665A | f14 | 4 | 4 | 2025-01-02 | 2025-04-23 | 112 | 312 | 2.786
e25 | 530N02673A | f11 | 4 | 4 | 2025-01-20 | 2025-03-22 | 62 | 101 | 1.629
e26 | 530N02695A | f14 | 4 | 4 | 2025-03-10 | 2025-06-17 | 100 | 341 | 3.41
e27 | 530N02704A | f14 | 4 | 4 | 2025-01-01 | 2025-04-25 | 115 | 276 | 2.4
e28 | 530N02705A | f14 | 4 | 4 | 2025-01-08 | 2025-03-18 | 70 | 156 | 2.229
e29 | 530N02710A | f14 | 4 | 4 | 2025-04-02 | 2025-06-11 | 71 | 323 | 4.549
e3 | 530L00935A | f3 | 4 | 4 | 2025-01-31 | 2025-02-13 | 14 | 42 | 3
e30 | 530N02712A | f14 | 4 | 4 | 2025-03-30 | 2025-05-28 | 60 | 105 | 1.75
e31 | 530N02714A | f14 | 4 | 4 | 2025-03-07 | 2025-05-08 | 63 | 148 | 2.349
e32 | 530N02716A | f14 | 4 | 4 | 2025-01-20 | 2025-03-12 | 52 | 90 | 1.731
e33 | 530N02717A | f14 | 4 | 4 | 2025-02-13 | 2025-05-08 | 85 | 170 | 2
e34 | 530N02753A | f4 | 4 | 4 | 2025-01-01 | 2025-03-08 | 67 | 204 | 3.045
e35 | 530N02757A | f15 | 4 | 4 | 2025-03-26 | 2025-05-29 | 65 | 207 | 3.185
e36 | 530N02759A | f15 | 4 | 4 | 2025-08-12 | 2025-09-24 | 44 | 98 | 2.227
e37 | 530N02760A | f15 | 4 | 4 | 2025-04-07 | 2025-06-09 | 64 | 160 | 2.5
e38 | 530N02761A | f15 | 4 | 4 | 2025-05-08 | 2025-06-12 | 36 | 119 | 3.306
e39 | 530N02780A | f16 | 4 | 4 | 2025-05-16 | 2025-07-23 | 69 | 179 | 2.594
e4 | 530L00936A | f3 | 4 | 4 | 2025-01-23 | 2025-03-20 | 57 | 62 | 1.088
e40 | 530N02782A | f16 | 4 | 4 | 2025-05-12 | 2025-10-09 | 151 | 374 | 2.477
e41 | 530N02783A | f16 | 4 | 4 | 2025-05-09 | 2025-08-01 | 85 | 208 | 2.447
e42 | 530N02799A | f10 | 4 | 4 | 2025-12-11 | 2026-02-16 | 68 | 47 | 0.691
e43 | 530N02801A | f17 | 4 | 4 | 2025-07-25 | 2025-09-10 | 48 | 282 | 5.875
e44 | 530N02802A | f18 | 4 | 4 | 2025-03-24 | 2025-08-02 | 132 | 232 | 1.758
e45 | 530N02817A | f6 | 4 | 4 | 2025-05-19 | 2025-07-26 | 69 | 244 | 3.536
e46 | 530N02818A | f19 | 4 | 4 | 2026-02-23 | 2026-03-31 | 37 | 232 | 6.27
e47 | 530N02819A | f20 | 4 | 4 | 2025-04-09 | 2025-07-24 | 107 | 208 | 1.944
e48 | 530N02822A | f18 | 4 | 4 | 2025-04-10 | 2025-07-05 | 87 | 259 | 2.977
e49 | 530N02824A | f4 | 4 | 4 | 2025-02-24 | 2025-04-10 | 46 | 123 | 2.674
e5 | 530L00938A | f3 | 4 | 4 | 2025-01-20 | 2025-04-09 | 80 | 250 | 3.125
e50 | 530N02846A | f21 | 4 | 4 | 2025-03-24 | 2025-04-02 | 10 | 10 | 1
e51 | 530N02848A | f22 | 4 | 4 | 2025-07-17 | 2025-11-13 | 120 | 299 | 2.492
e52 | 530N02849A | f17 | 4 | 4 | 2025-08-19 | 2025-11-16 | 90 | 256 | 2.844
e53 | 530N02876A | f23 | 4 | 4 | 2025-12-30 | 2026-01-30 | 32 | 130 | 4.062
e54 | 530N02887A | f23 | 4 | 4 | 2025-11-14 | 2025-12-10 | 27 | 38 | 1.407
e55 | 530N02888A | f23 | 4 | 4 | 2025-11-20 | 2025-12-16 | 27 | 53 | 1.963
e56 | 530N02914A | f18 | 4 | 4 | 2025-08-05 | 2025-12-21 | 139 | 275 | 1.978
e57 | 530N02920A | f24 | 4 | 4 | 2025-06-12 | 2025-08-22 | 72 | 218 | 3.028
e58 | 530N02921A | f24 | 4 | 4 | 2025-06-13 | 2025-08-22 | 71 | 207 | 2.915
e59 | 530N02923A | f16 | 4 | 4 | 2025-04-15 | 2025-08-19 | 127 | 589 | 4.638
e6 | 530L00940A | f4 | 4 | 4 | 2025-03-26 | 2025-06-30 | 97 | 121 | 1.247
e60 | 530N02924A | f16 | 4 | 4 | 2025-05-13 | 2025-08-30 | 110 | 461 | 4.191
e61 | 530N02930A | f16 | 4 | 4 | 2025-11-03 | 2025-11-07 | 5 | 5 | 1
e62 | 530N02934A | f16 | 4 | 4 | 2025-07-05 | 2025-07-26 | 22 | 22 | 1
e63 | 530N02959A | f25 | 4 | 4 | 2025-11-21 | 2025-12-13 | 23 | 23 | 1
e64 | 530N02971A | f14 | 4 | 4 | 2025-09-19 | 2025-12-25 | 98 | 171 | 1.745
e65 | 530N03002A | f26 | 4 | 4 | 2025-10-30 | 2026-01-16 | 79 | 239 | 3.025
e66 | 530N03014A | f14 | 4 | 4 | 2025-11-18 | 2026-03-16 | 119 | 88 | 0.739
e67 | 530N03065A | f27 | 4 | 4 | 2025-11-20 | 2026-03-21 | 122 | 303 | 2.484
e68 | 530N03073A | f28 | 4 | 4 | 2025-11-11 | 2026-01-13 | 64 | 375 | 5.859
e69 | 530N03074A | f28 | 4 | 4 | 2025-11-06 | 2026-01-13 | 69 | 366 | 5.304
e7 | 530N02075A | f5 | 4 | 4 | 2025-01-01 | 2025-03-07 | 66 | 80 | 1.212
e70 | 530N03075A | f14 | 4 | 4 | 2025-12-04 | 2025-12-25 | 22 | 40 | 1.818
e71 | 530N03081A | f14 | 4 | 4 | 2025-10-06 | 2026-01-19 | 106 | 161 | 1.519
e72 | 530N03082A | f29 | 4 | 4 | 2025-10-24 | 2026-03-13 | 141 | 524 | 3.716
e73 | 530N03107A | f30 | 4 | 4 | 2025-09-18 | 2025-12-27 | 101 | 435 | 4.307
e74 | 530N03156A | f31 | 4 | 4 | 2026-01-14 | 2026-03-27 | 73 | 338 | 4.63
e75 | 830300168A | f32 | 4 | 4 | 2025-01-07 | 2025-07-25 | 200 | 462 | 2.31
e76 | 830300171A | f22 | 4 | 4 | 2025-01-06 | 2025-02-14 | 40 | 131 | 3.275
e77 | 830300176A | f17 | 4 | 4 | 2025-01-01 | 2025-01-06 | 6 | 6 | 1
e78 | 830300178A | f33 | 4 | 4 | 2025-02-03 | 2025-03-22 | 48 | 202 | 4.208
e79 | 830300179A | f22 | 4 | 4 | 2025-02-04 | 2025-05-31 | 117 | 621 | 5.308
e8 | 530N02385A | f6 | 4 | 4 | 2025-01-08 | 2025-02-27 | 51 | 219 | 4.294
e80 | 830300180A | f17 | 4 | 4 | 2025-02-14 | 2025-05-17 | 93 | 205 | 2.204
e81 | 830300182A | f17 | 4 | 4 | 2025-03-07 | 2025-05-06 | 61 | 190 | 3.115
e82 | 830300183A | f31 | 4 | 4 | 2025-01-11 | 2025-03-21 | 70 | 304 | 4.343
e83 | 830300184A | f17 | 4 | 4 | 2025-03-14 | 2025-06-14 | 93 | 189 | 2.032
e84 | 830300185A | f17 | 4 | 4 | 2025-03-23 | 2025-06-27 | 97 | 219 | 2.258
e85 | 830300186A | f17 | 4 | 4 | 2025-05-21 | 2025-07-25 | 66 | 66 | 1
e86 | 830300188A | f34 | 4 | 4 | 2025-06-30 | 2025-09-30 | 93 | 381 | 4.097
e87 | 830300189A | f22 | 4 | 4 | 2025-08-25 | 2025-08-31 | 7 | 84 | 12
e88 | 830300192A | f35 | 4 | 4 | 2025-05-14 | 2025-05-26 | 13 | 25 | 1.923
e89 | 830300193A | f31 | 4 | 4 | 2025-03-24 | 2025-05-29 | 67 | 304 | 4.537
e9 | 530N02534A | f7 | 4 | 4 | 2025-01-03 | 2025-01-28 | 26 | 26 | 1
e90 | 830300198A | f31 | 4 | 4 | 2025-07-05 | 2025-08-30 | 57 | 246 | 4.316
e91 | 830300201A | f17 | 4 | 4 | 2025-07-17 | 2025-09-20 | 66 | 192 | 2.909
e92 | 830300202A | f30 | 4 | 4 | 2025-09-01 | 2025-12-24 | 115 | 118 | 1.026
e93 | 830300204A | f31 | 4 | 4 | 2025-07-11 | 2025-10-25 | 107 | 377 | 3.523
e94 | 830300205A | f31 | 4 | 4 | 2025-07-12 | 2025-11-28 | 140 | 475 | 3.393
e95 | 830400201A | f13 | 4 | 4 | 2025-01-01 | 2025-02-14 | 45 | 131 | 2.911
e96 | 830400202A | f36 | 4 | 4 | 2025-01-01 | 2025-01-05 | 5 | 10 | 2
e97 | 830400204A | f14 | 4 | 4 | 2025-01-03 | 2025-04-19 | 107 | 491 | 4.589
e98 | 830400211A | f15 | 4 | 4 | 2025-04-07 | 2025-06-09 | 64 | 75 | 1.172
e99 | 830400225A | f37 | 4 | 4 | 2025-10-21 | 2026-01-17 | 89 | 343 | 3.854

## Distributions
operation | workload_range | count
p1 | 0-25 | 36
p1 | 100-150 | 21
p1 | 1000+ | 0
p1 | 150-200 | 5
p1 | 200-300 | 4
p1 | 25-50 | 18
p1 | 300-500 | 1
p1 | 50-75 | 15
p1 | 500-1000 | 0
p1 | 75-100 | 10
p2 | 0-25 | 32
p2 | 100-150 | 15
p2 | 1000+ | 0
p2 | 150-200 | 8
p2 | 200-300 | 5
p2 | 25-50 | 22
p2 | 300-500 | 0
p2 | 50-75 | 20
p2 | 500-1000 | 0
p2 | 75-100 | 8
p3 | 0-25 | 48
p3 | 100-150 | 3
p3 | 1000+ | 0
p3 | 150-200 | 1
p3 | 200-300 | 0
p3 | 25-50 | 34
p3 | 300-500 | 0
p3 | 50-75 | 16
p3 | 500-1000 | 0
p3 | 75-100 | 8
p4 | 0-25 | 53
p4 | 100-150 | 1
p4 | 1000+ | 0
p4 | 150-200 | 2
p4 | 200-300 | 1
p4 | 25-50 | 33
p4 | 300-500 | 0
p4 | 50-75 | 12
p4 | 500-1000 | 1
p4 | 75-100 | 7

## Data (op tasks)
module_id | module_name | fab | phase_id | phase_name | operation | operation_task_id | operation_task_name | start_date | end_date | duration_days | workload_days | intensity_workload_per_day
e1 | 530900102A | f1 | tool_p1 | Module Setup | p1 | e1_p1 | Module Setup | 2025/10/14 | 2025/11/27 | 45 | 236 | 5.2444
e1 | 530900102A | f1 | tool_p2 | Hardware Setup | p2 | e1_p2 | Hardware Setup | 2025/11/28 | 2025/12/17 | 20 | 70 | 3.5
e1 | 530900102A | f1 | tool_p3 | Function Setup | p3 | e1_p3 | Function Setup | 2025/12/18 | 2026/01/18 | 32 | 57 | 1.7812
e1 | 530900102A | f1 | tool_p4 | Utility | p4 | e1_p4 | Utility | 2026/01/19 | 2026/01/30 | 12 | 34 | 2.8333
e2 | 530900112A | f2 | tool_p1 | Module Setup | p1 | e2_p1 | Module Setup | 2025/11/05 | 2025/11/20 | 16 | 100 | 6.25
e2 | 530900112A | f2 | tool_p2 | Hardware Setup | p2 | e2_p2 | Hardware Setup | 2025/11/21 | 2025/12/10 | 20 | 131 | 6.55
e2 | 530900112A | f2 | tool_p3 | Function Setup | p3 | e2_p3 | Function Setup | 2025/12/11 | 2025/12/22 | 12 | 60 | 5
e2 | 530900112A | f2 | tool_p4 | Utility | p4 | e2_p4 | Utility | 2025/12/23 | 2026/01/16 | 25 | 55 | 2.2
e3 | 530L00935A | f3 | tool_p1 | Module Setup | p1 | e3_p1 | Module Setup | 2025/01/31 | 2025/02/03 | 4 | 10 | 2.5
e3 | 530L00935A | f3 | tool_p2 | Hardware Setup | p2 | e3_p2 | Hardware Setup | 2025/02/04 | 2025/02/07 | 4 | 15 | 3.75
e3 | 530L00935A | f3 | tool_p3 | Function Setup | p3 | e3_p3 | Function Setup | 2025/02/08 | 2025/02/10 | 3 | 9 | 3
e3 | 530L00935A | f3 | tool_p4 | Utility | p4 | e3_p4 | Utility | 2025/02/11 | 2025/02/13 | 3 | 8 | 2.6667
e4 | 530L00936A | f3 | tool_p1 | Module Setup | p1 | e4_p1 | Module Setup | 2025/01/23 | 2025/02/06 | 15 | 15 | 1
e4 | 530L00936A | f3 | tool_p2 | Hardware Setup | p2 | e4_p2 | Hardware Setup | 2025/02/07 | 2025/02/20 | 14 | 22 | 1.5714
e4 | 530L00936A | f3 | tool_p3 | Function Setup | p3 | e4_p3 | Function Setup | 2025/02/21 | 2025/03/08 | 16 | 13 | 0.8125
e4 | 530L00936A | f3 | tool_p4 | Utility | p4 | e4_p4 | Utility | 2025/03/09 | 2025/03/20 | 12 | 12 | 1
e5 | 530L00938A | f3 | tool_p1 | Module Setup | p1 | e5_p1 | Module Setup | 2025/01/20 | 2025/02/12 | 24 | 85 | 3.5417
e5 | 530L00938A | f3 | tool_p2 | Hardware Setup | p2 | e5_p2 | Hardware Setup | 2025/02/13 | 2025/03/07 | 23 | 27 | 1.1739
e5 | 530L00938A | f3 | tool_p3 | Function Setup | p3 | e5_p3 | Function Setup | 2025/03/08 | 2025/03/21 | 14 | 71 | 5.0714
e5 | 530L00938A | f3 | tool_p4 | Utility | p4 | e5_p4 | Utility | 2025/03/22 | 2025/04/09 | 19 | 67 | 3.5263
e6 | 530L00940A | f4 | tool_p1 | Module Setup | p1 | e6_p1 | Module Setup | 2025/03/26 | 2025/04/01 | 7 | 25 | 3.5714
e6 | 530L00940A | f4 | tool_p2 | Hardware Setup | p2 | e6_p2 | Hardware Setup | 2025/04/02 | 2025/06/21 | 81 | 78 | 0.96296
e6 | 530L00940A | f4 | tool_p3 | Function Setup | p3 | e6_p3 | Function Setup | 2025/06/22 | 2025/06/27 | 6 | 12 | 2
e6 | 530L00940A | f4 | tool_p4 | Utility | p4 | e6_p4 | Utility | 2025/06/28 | 2025/06/30 | 3 | 6 | 2
e7 | 530N02075A | f5 | tool_p1 | Module Setup | p1 | e7_p1 | Module Setup | 2025/01/01 | 2025/01/21 | 21 | 35 | 1.6667
e7 | 530N02075A | f5 | tool_p2 | Hardware Setup | p2 | e7_p2 | Hardware Setup | 2025/01/22 | 2025/02/15 | 25 | 25 | 1
e7 | 530N02075A | f5 | tool_p3 | Function Setup | p3 | e7_p3 | Function Setup | 2025/02/16 | 2025/02/28 | 13 | 13 | 1
e7 | 530N02075A | f5 | tool_p4 | Utility | p4 | e7_p4 | Utility | 2025/03/01 | 2025/03/07 | 7 | 7 | 1
e8 | 530N02385A | f6 | tool_p1 | Module Setup | p1 | e8_p1 | Module Setup | 2025/01/08 | 2025/01/11 | 4 | 16 | 4
e8 | 530N02385A | f6 | tool_p2 | Hardware Setup | p2 | e8_p2 | Hardware Setup | 2025/01/12 | 2025/01/16 | 5 | 20 | 4
e8 | 530N02385A | f6 | tool_p3 | Function Setup | p3 | e8_p3 | Function Setup | 2025/01/17 | 2025/01/20 | 4 | 16 | 4
e8 | 530N02385A | f6 | tool_p4 | Utility | p4 | e8_p4 | Utility | 2025/01/21 | 2025/02/27 | 38 | 167 | 4.3947
e9 | 530N02534A | f7 | tool_p1 | Module Setup | p1 | e9_p1 | Module Setup | 2025/01/03 | 2025/01/11 | 9 | 9 | 1
e9 | 530N02534A | f7 | tool_p2 | Hardware Setup | p2 | e9_p2 | Hardware Setup | 2025/01/12 | 2025/01/18 | 7 | 7 | 1
e9 | 530N02534A | f7 | tool_p3 | Function Setup | p3 | e9_p3 | Function Setup | 2025/01/19 | 2025/01/21 | 3 | 3 | 1
e9 | 530N02534A | f7 | tool_p4 | Utility | p4 | e9_p4 | Utility | 2025/01/22 | 2025/01/28 | 7 | 7 | 1
e10 | 530N02566A | f8 | tool_p1 | Module Setup | p1 | e10_p1 | Module Setup | 2026/01/21 | 2026/02/18 | 29 | 63 | 2.1724
e10 | 530N02566A | f8 | tool_p2 | Hardware Setup | p2 | e10_p2 | Hardware Setup | 2026/02/19 | 2026/03/05 | 15 | 33 | 2.2
e10 | 530N02566A | f8 | tool_p3 | Function Setup | p3 | e10_p3 | Function Setup | 2026/03/06 | 2026/03/14 | 9 | 18 | 2
e10 | 530N02566A | f8 | tool_p4 | Utility | p4 | e10_p4 | Utility | 2026/03/15 | 2026/03/31 | 17 | 20 | 1.1765
e11 | 530N02609A | f9 | tool_p1 | Module Setup | p1 | e11_p1 | Module Setup | 2025/01/01 | 2025/01/05 | 5 | 9 | 1.8
e11 | 530N02609A | f9 | tool_p2 | Hardware Setup | p2 | e11_p2 | Hardware Setup | 2025/01/06 | 2025/01/16 | 11 | 7 | 0.63636
e11 | 530N02609A | f9 | tool_p3 | Function Setup | p3 | e11_p3 | Function Setup | 2025/01/17 | 2025/01/21 | 5 | 19 | 3.8
e11 | 530N02609A | f9 | tool_p4 | Utility | p4 | e11_p4 | Utility | 2025/01/22 | 2025/01/24 | 3 | 12 | 4
e12 | 530N02615A | f3 | tool_p1 | Module Setup | p1 | e12_p1 | Module Setup | 2025/01/08 | 2025/01/16 | 9 | 58 | 6.4444
e12 | 530N02615A | f3 | tool_p2 | Hardware Setup | p2 | e12_p2 | Hardware Setup | 2025/01/17 | 2025/01/23 | 7 | 60 | 8.5714
e12 | 530N02615A | f3 | tool_p3 | Function Setup | p3 | e12_p3 | Function Setup | 2025/01/24 | 2025/01/31 | 8 | 30 | 3.75
e12 | 530N02615A | f3 | tool_p4 | Utility | p4 | e12_p4 | Utility | 2025/02/01 | 2025/02/13 | 13 | 27 | 2.0769
e13 | 530N02616A | f3 | tool_p1 | Module Setup | p1 | e13_p1 | Module Setup | 2025/01/31 | 2025/02/08 | 9 | 9 | 1
e13 | 530N02616A | f3 | tool_p2 | Hardware Setup | p2 | e13_p2 | Hardware Setup | 2025/02/09 | 2025/02/14 | 6 | 6 | 1
e13 | 530N02616A | f3 | tool_p3 | Function Setup | p3 | e13_p3 | Function Setup | 2025/02/19 | 2025/02/26 | 8 | 8 | 1
e13 | 530N02616A | f3 | tool_p4 | Utility | p4 | e13_p4 | Utility | 2025/02/27 | 2025/03/10 | 12 | 12 | 1
e14 | 530N02620A | f3 | tool_p1 | Module Setup | p1 | e14_p1 | Module Setup | 2025/02/20 | 2025/02/27 | 8 | 15 | 1.875
e14 | 530N02620A | f3 | tool_p2 | Hardware Setup | p2 | e14_p2 | Hardware Setup | 2025/02/28 | 2025/03/04 | 5 | 10 | 2
e14 | 530N02620A | f3 | tool_p3 | Function Setup | p3 | e14_p3 | Function Setup | 2025/03/05 | 2025/03/10 | 6 | 16 | 2.6667
e14 | 530N02620A | f3 | tool_p4 | Utility | p4 | e14_p4 | Utility | 2025/03/11 | 2025/03/21 | 11 | 25 | 2.2727
e15 | 530N02622A | f10 | tool_p1 | Module Setup | p1 | e15_p1 | Module Setup | 2025/02/09 | 2025/03/28 | 48 | 135 | 2.8125
e15 | 530N02622A | f10 | tool_p2 | Hardware Setup | p2 | e15_p2 | Hardware Setup | 2025/03/29 | 2025/05/26 | 59 | 22 | 0.37288
e15 | 530N02622A | f10 | tool_p3 | Function Setup | p3 | e15_p3 | Function Setup | 2025/05/27 | 2025/06/15 | 20 | 36 | 1.8
e15 | 530N02622A | f10 | tool_p4 | Utility | p4 | e15_p4 | Utility | 2025/06/16 | 2025/07/23 | 38 | 97 | 2.5526
e16 | 530N02623A | f10 | tool_p1 | Module Setup | p1 | e16_p1 | Module Setup | 2025/01/31 | 2025/02/17 | 18 | 111 | 6.1667
e16 | 530N02623A | f10 | tool_p2 | Hardware Setup | p2 | e16_p2 | Hardware Setup | 2025/02/18 | 2025/03/03 | 14 | 150 | 10.7143
e16 | 530N02623A | f10 | tool_p3 | Function Setup | p3 | e16_p3 | Function Setup | 2025/03/04 | 2025/03/11 | 8 | 98 | 12.25
e16 | 530N02623A | f10 | tool_p4 | Utility | p4 | e16_p4 | Utility | 2025/03/12 | 2025/06/29 | 110 | 683 | 6.2091
e17 | 530N02624A | f10 | tool_p1 | Module Setup | p1 | e17_p1 | Module Setup | 2025/03/04 | 2025/03/23 | 20 | 38 | 1.9
e17 | 530N02624A | f10 | tool_p2 | Hardware Setup | p2 | e17_p2 | Hardware Setup | 2025/03/24 | 2025/05/10 | 48 | 41 | 0.85417
e17 | 530N02624A | f10 | tool_p3 | Function Setup | p3 | e17_p3 | Function Setup | 2025/05/11 | 2025/06/01 | 22 | 27 | 1.2273
e17 | 530N02624A | f10 | tool_p4 | Utility | p4 | e17_p4 | Utility | 2025/06/02 | 2025/08/11 | 71 | 144 | 2.0282
e18 | 530N02626A | f11 | tool_p1 | Module Setup | p1 | e18_p1 | Module Setup | 2025/01/01 | 2025/01/14 | 14 | 22 | 1.5714
e18 | 530N02626A | f11 | tool_p2 | Hardware Setup | p2 | e18_p2 | Hardware Setup | 2025/01/15 | 2025/02/13 | 30 | 21 | 0.7
e18 | 530N02626A | f11 | tool_p3 | Function Setup | p3 | e18_p3 | Function Setup | 2025/02/14 | 2025/02/26 | 13 | 50 | 3.8462
e18 | 530N02626A | f11 | tool_p4 | Utility | p4 | e18_p4 | Utility | 2025/02/27 | 2025/03/04 | 6 | 15 | 2.5
e19 | 530N02628A | f11 | tool_p1 | Module Setup | p1 | e19_p1 | Module Setup | 2025/01/01 | 2025/01/22 | 22 | 93 | 4.2273
e19 | 530N02628A | f11 | tool_p2 | Hardware Setup | p2 | e19_p2 | Hardware Setup | 2025/01/23 | 2025/02/28 | 37 | 152 | 4.1081
e19 | 530N02628A | f11 | tool_p3 | Function Setup | p3 | e19_p3 | Function Setup | 2025/03/01 | 2025/03/21 | 21 | 56 | 2.6667
e19 | 530N02628A | f11 | tool_p4 | Utility | p4 | e19_p4 | Utility | 2025/03/22 | 2025/04/01 | 11 | 15 | 1.3636
e20 | 530N02632A | f12 | tool_p1 | Module Setup | p1 | e20_p1 | Module Setup | 2025/04/02 | 2025/04/03 | 2 | 2 | 1
e20 | 530N02632A | f12 | tool_p2 | Hardware Setup | p2 | e20_p2 | Hardware Setup | 2025/04/04 | 2025/04/04 | 1 | 1 | 1
e20 | 530N02632A | f12 | tool_p3 | Function Setup | p3 | e20_p3 | Function Setup | 2025/04/05 | 2025/04/05 | 1 | 1 | 1
e20 | 530N02632A | f12 | tool_p4 | Utility | p4 | e20_p4 | Utility | 2025/04/06 | 2025/04/06 | 1 | 1 | 1
e21 | 530N02635A | f3 | tool_p1 | Module Setup | p1 | e21_p1 | Module Setup | 2025/05/07 | 2025/06/17 | 42 | 178 | 4.2381
e21 | 530N02635A | f3 | tool_p2 | Hardware Setup | p2 | e21_p2 | Hardware Setup | 2025/06/18 | 2025/07/07 | 20 | 73 | 3.65
e21 | 530N02635A | f3 | tool_p3 | Function Setup | p3 | e21_p3 | Function Setup | 2025/07/08 | 2025/07/17 | 10 | 28 | 2.8
e21 | 530N02635A | f3 | tool_p4 | Utility | p4 | e21_p4 | Utility | 2025/07/18 | 2025/07/24 | 7 | 9 | 1.2857
e22 | 530N02639A | f6 | tool_p1 | Module Setup | p1 | e22_p1 | Module Setup | 2025/01/23 | 2025/02/07 | 16 | 119 | 7.4375
e22 | 530N02639A | f6 | tool_p2 | Hardware Setup | p2 | e22_p2 | Hardware Setup | 2025/02/08 | 2025/02/18 | 11 | 82 | 7.4545
e22 | 530N02639A | f6 | tool_p3 | Function Setup | p3 | e22_p3 | Function Setup | 2025/02/19 | 2025/03/01 | 11 | 30 | 2.7273
e22 | 530N02639A | f6 | tool_p4 | Utility | p4 | e22_p4 | Utility | 2025/03/02 | 2025/03/10 | 9 | 18 | 2
e23 | 530N02646A | f13 | tool_p1 | Module Setup | p1 | e23_p1 | Module Setup | 2025/01/01 | 2025/01/05 | 5 | 5 | 1
e23 | 530N02646A | f13 | tool_p2 | Hardware Setup | p2 | e23_p2 | Hardware Setup | 2025/01/06 | 2025/01/10 | 5 | 5 | 1
e23 | 530N02646A | f13 | tool_p3 | Function Setup | p3 | e23_p3 | Function Setup | 2025/01/11 | 2025/01/11 | 1 | 1 | 1
e23 | 530N02646A | f13 | tool_p4 | Utility | p4 | e23_p4 | Utility | 2025/01/12 | 2025/01/18 | 7 | 7 | 1
e24 | 530N02665A | f14 | tool_p1 | Module Setup | p1 | e24_p1 | Module Setup | 2025/01/02 | 2025/02/02 | 32 | 160 | 5
e24 | 530N02665A | f14 | tool_p2 | Hardware Setup | p2 | e24_p2 | Hardware Setup | 2025/02/03 | 2025/02/25 | 23 | 70 | 3.0435
e24 | 530N02665A | f14 | tool_p3 | Function Setup | p3 | e24_p3 | Function Setup | 2025/02/26 | 2025/03/18 | 21 | 41 | 1.9524
e24 | 530N02665A | f14 | tool_p4 | Utility | p4 | e24_p4 | Utility | 2025/03/19 | 2025/04/23 | 36 | 41 | 1.1389
e25 | 530N02673A | f11 | tool_p1 | Module Setup | p1 | e25_p1 | Module Setup | 2025/01/20 | 2025/02/23 | 35 | 26 | 0.74286
e25 | 530N02673A | f11 | tool_p2 | Hardware Setup | p2 | e25_p2 | Hardware Setup | 2025/02/24 | 2025/03/04 | 9 | 27 | 3
e25 | 530N02673A | f11 | tool_p3 | Function Setup | p3 | e25_p3 | Function Setup | 2025/03/05 | 2025/03/13 | 9 | 26 | 2.8889
e25 | 530N02673A | f11 | tool_p4 | Utility | p4 | e25_p4 | Utility | 2025/03/14 | 2025/03/22 | 9 | 22 | 2.4444
e26 | 530N02695A | f14 | tool_p1 | Module Setup | p1 | e26_p1 | Module Setup | 2025/03/10 | 2025/04/01 | 23 | 113 | 4.913
e26 | 530N02695A | f14 | tool_p2 | Hardware Setup | p2 | e26_p2 | Hardware Setup | 2025/04/02 | 2025/04/27 | 26 | 155 | 5.9615
e26 | 530N02695A | f14 | tool_p3 | Function Setup | p3 | e26_p3 | Function Setup | 2025/04/28 | 2025/05/13 | 16 | 46 | 2.875
e26 | 530N02695A | f14 | tool_p4 | Utility | p4 | e26_p4 | Utility | 2025/05/14 | 2025/06/17 | 35 | 27 | 0.77143
e27 | 530N02704A | f14 | tool_p1 | Module Setup | p1 | e27_p1 | Module Setup | 2025/01/01 | 2025/01/13 | 13 | 35 | 2.6923
e27 | 530N02704A | f14 | tool_p2 | Hardware Setup | p2 | e27_p2 | Hardware Setup | 2025/01/14 | 2025/02/11 | 29 | 92 | 3.1724
e27 | 530N02704A | f14 | tool_p3 | Function Setup | p3 | e27_p3 | Function Setup | 2025/02/12 | 2025/03/15 | 32 | 61 | 1.9062
e27 | 530N02704A | f14 | tool_p4 | Utility | p4 | e27_p4 | Utility | 2025/03/16 | 2025/04/25 | 41 | 88 | 2.1463
e28 | 530N02705A | f14 | tool_p1 | Module Setup | p1 | e28_p1 | Module Setup | 2025/01/08 | 2025/01/14 | 7 | 14 | 2
e28 | 530N02705A | f14 | tool_p2 | Hardware Setup | p2 | e28_p2 | Hardware Setup | 2025/01/15 | 2025/01/22 | 8 | 26 | 3.25
e28 | 530N02705A | f14 | tool_p3 | Function Setup | p3 | e28_p3 | Function Setup | 2025/01/23 | 2025/01/27 | 5 | 24 | 4.8
e28 | 530N02705A | f14 | tool_p4 | Utility | p4 | e28_p4 | Utility | 2025/01/28 | 2025/03/18 | 50 | 92 | 1.84
e29 | 530N02710A | f14 | tool_p1 | Module Setup | p1 | e29_p1 | Module Setup | 2025/04/02 | 2025/04/20 | 19 | 113 | 5.9474
e29 | 530N02710A | f14 | tool_p2 | Hardware Setup | p2 | e29_p2 | Hardware Setup | 2025/04/21 | 2025/05/12 | 22 | 134 | 6.0909
e29 | 530N02710A | f14 | tool_p3 | Function Setup | p3 | e29_p3 | Function Setup | 2025/05/13 | 2025/05/25 | 13 | 49 | 3.7692
e29 | 530N02710A | f14 | tool_p4 | Utility | p4 | e29_p4 | Utility | 2025/05/26 | 2025/06/11 | 17 | 27 | 1.5882
e30 | 530N02712A | f14 | tool_p1 | Module Setup | p1 | e30_p1 | Module Setup | 2025/03/30 | 2025/04/04 | 6 | 14 | 2.3333
e30 | 530N02712A | f14 | tool_p2 | Hardware Setup | p2 | e30_p2 | Hardware Setup | 2025/04/05 | 2025/04/11 | 7 | 21 | 3
e30 | 530N02712A | f14 | tool_p3 | Function Setup | p3 | e30_p3 | Function Setup | 2025/04/12 | 2025/04/13 | 2 | 6 | 3
e30 | 530N02712A | f14 | tool_p4 | Utility | p4 | e30_p4 | Utility | 2025/04/14 | 2025/05/28 | 45 | 64 | 1.4222
e31 | 530N02714A | f14 | tool_p1 | Module Setup | p1 | e31_p1 | Module Setup | 2025/03/07 | 2025/03/22 | 16 | 45 | 2.8125
e31 | 530N02714A | f14 | tool_p2 | Hardware Setup | p2 | e31_p2 | Hardware Setup | 2025/03/23 | 2025/04/10 | 19 | 51 | 2.6842
e31 | 530N02714A | f14 | tool_p3 | Function Setup | p3 | e31_p3 | Function Setup | 2025/04/11 | 2025/04/22 | 12 | 21 | 1.75
e31 | 530N02714A | f14 | tool_p4 | Utility | p4 | e31_p4 | Utility | 2025/04/23 | 2025/05/08 | 16 | 31 | 1.9375
e32 | 530N02716A | f14 | tool_p1 | Module Setup | p1 | e32_p1 | Module Setup | 2025/01/20 | 2025/02/02 | 14 | 26 | 1.8571
e32 | 530N02716A | f14 | tool_p2 | Hardware Setup | p2 | e32_p2 | Hardware Setup | 2025/02/03 | 2025/02/18 | 16 | 32 | 2
e32 | 530N02716A | f14 | tool_p3 | Function Setup | p3 | e32_p3 | Function Setup | 2025/02/19 | 2025/02/27 | 9 | 18 | 2
e32 | 530N02716A | f14 | tool_p4 | Utility | p4 | e32_p4 | Utility | 2025/02/28 | 2025/03/12 | 13 | 14 | 1.0769
e33 | 530N02717A | f14 | tool_p1 | Module Setup | p1 | e33_p1 | Module Setup | 2025/02/13 | 2025/03/05 | 21 | 37 | 1.7619
e33 | 530N02717A | f14 | tool_p2 | Hardware Setup | p2 | e33_p2 | Hardware Setup | 2025/03/06 | 2025/04/01 | 27 | 53 | 1.963
e33 | 530N02717A | f14 | tool_p3 | Function Setup | p3 | e33_p3 | Function Setup | 2025/04/02 | 2025/04/15 | 14 | 33 | 2.3571
e33 | 530N02717A | f14 | tool_p4 | Utility | p4 | e33_p4 | Utility | 2025/04/16 | 2025/05/08 | 23 | 47 | 2.0435
e34 | 530N02753A | f4 | tool_p1 | Module Setup | p1 | e34_p1 | Module Setup | 2025/01/01 | 2025/01/08 | 8 | 50 | 6.25
e34 | 530N02753A | f4 | tool_p2 | Hardware Setup | p2 | e34_p2 | Hardware Setup | 2025/01/09 | 2025/01/25 | 17 | 83 | 4.8824
e34 | 530N02753A | f4 | tool_p3 | Function Setup | p3 | e34_p3 | Function Setup | 2025/01/26 | 2025/02/20 | 26 | 55 | 2.1154
e34 | 530N02753A | f4 | tool_p4 | Utility | p4 | e34_p4 | Utility | 2025/02/21 | 2025/03/08 | 16 | 16 | 1
e35 | 530N02757A | f15 | tool_p1 | Module Setup | p1 | e35_p1 | Module Setup | 2025/03/26 | 2025/04/16 | 22 | 103 | 4.6818
e35 | 530N02757A | f15 | tool_p2 | Hardware Setup | p2 | e35_p2 | Hardware Setup | 2025/04/17 | 2025/05/04 | 18 | 59 | 3.2778
e35 | 530N02757A | f15 | tool_p3 | Function Setup | p3 | e35_p3 | Function Setup | 2025/05/05 | 2025/05/12 | 8 | 16 | 2
e35 | 530N02757A | f15 | tool_p4 | Utility | p4 | e35_p4 | Utility | 2025/05/13 | 2025/05/29 | 17 | 29 | 1.7059
e36 | 530N02759A | f15 | tool_p1 | Module Setup | p1 | e36_p1 | Module Setup | 2025/08/12 | 2025/08/25 | 14 | 44 | 3.1429
e36 | 530N02759A | f15 | tool_p2 | Hardware Setup | p2 | e36_p2 | Hardware Setup | 2025/08/26 | 2025/09/06 | 12 | 36 | 3
e36 | 530N02759A | f15 | tool_p3 | Function Setup | p3 | e36_p3 | Function Setup | 2025/09/09 | 2025/09/13 | 5 | 5 | 1
e36 | 530N02759A | f15 | tool_p4 | Utility | p4 | e36_p4 | Utility | 2025/09/14 | 2025/09/24 | 11 | 13 | 1.1818
e37 | 530N02760A | f15 | tool_p1 | Module Setup | p1 | e37_p1 | Module Setup | 2025/04/07 | 2025/04/28 | 22 | 80 | 3.6364
e37 | 530N02760A | f15 | tool_p2 | Hardware Setup | p2 | e37_p2 | Hardware Setup | 2025/04/29 | 2025/05/15 | 17 | 51 | 3
e37 | 530N02760A | f15 | tool_p3 | Function Setup | p3 | e37_p3 | Function Setup | 2025/05/16 | 2025/05/23 | 8 | 12 | 1.5
e37 | 530N02760A | f15 | tool_p4 | Utility | p4 | e37_p4 | Utility | 2025/05/24 | 2025/06/09 | 17 | 17 | 1
e38 | 530N02761A | f15 | tool_p1 | Module Setup | p1 | e38_p1 | Module Setup | 2025/05/08 | 2025/05/19 | 12 | 34 | 2.8333
e38 | 530N02761A | f15 | tool_p2 | Hardware Setup | p2 | e38_p2 | Hardware Setup | 2025/05/20 | 2025/05/29 | 10 | 33 | 3.3
e38 | 530N02761A | f15 | tool_p3 | Function Setup | p3 | e38_p3 | Function Setup | 2025/05/30 | 2025/06/02 | 4 | 17 | 4.25
e38 | 530N02761A | f15 | tool_p4 | Utility | p4 | e38_p4 | Utility | 2025/06/03 | 2025/06/12 | 10 | 35 | 3.5
e39 | 530N02780A | f16 | tool_p1 | Module Setup | p1 | e39_p1 | Module Setup | 2025/05/16 | 2025/06/04 | 20 | 72 | 3.6
e39 | 530N02780A | f16 | tool_p2 | Hardware Setup | p2 | e39_p2 | Hardware Setup | 2025/06/05 | 2025/06/18 | 14 | 45 | 3.2143
e39 | 530N02780A | f16 | tool_p3 | Function Setup | p3 | e39_p3 | Function Setup | 2025/06/19 | 2025/07/01 | 13 | 36 | 2.7692
e39 | 530N02780A | f16 | tool_p4 | Utility | p4 | e39_p4 | Utility | 2025/07/02 | 2025/07/23 | 22 | 26 | 1.1818
e40 | 530N02782A | f16 | tool_p1 | Module Setup | p1 | e40_p1 | Module Setup | 2025/05/12 | 2025/05/30 | 19 | 72 | 3.7895
e40 | 530N02782A | f16 | tool_p2 | Hardware Setup | p2 | e40_p2 | Hardware Setup | 2025/05/31 | 2025/08/02 | 64 | 222 | 3.4688
e40 | 530N02782A | f16 | tool_p3 | Function Setup | p3 | e40_p3 | Function Setup | 2025/08/03 | 2025/09/22 | 51 | 63 | 1.2353
e40 | 530N02782A | f16 | tool_p4 | Utility | p4 | e40_p4 | Utility | 2025/09/23 | 2025/10/09 | 17 | 17 | 1
e41 | 530N02783A | f16 | tool_p1 | Module Setup | p1 | e41_p1 | Module Setup | 2025/05/09 | 2025/05/24 | 16 | 53 | 3.3125
e41 | 530N02783A | f16 | tool_p2 | Hardware Setup | p2 | e41_p2 | Hardware Setup | 2025/05/25 | 2025/06/05 | 12 | 59 | 4.9167
e41 | 530N02783A | f16 | tool_p3 | Function Setup | p3 | e41_p3 | Function Setup | 2025/06/06 | 2025/07/31 | 56 | 95 | 1.6964
e41 | 530N02783A | f16 | tool_p4 | Utility | p4 | e41_p4 | Utility | 2025/08/01 | 2025/08/01 | 1 | 1 | 1
e42 | 530N02799A | f10 | tool_p1 | Module Setup | p1 | e42_p1 | Module Setup | 2025/12/11 | 2025/12/18 | 8 | 8 | 1
e42 | 530N02799A | f10 | tool_p2 | Hardware Setup | p2 | e42_p2 | Hardware Setup | 2025/12/19 | 2025/12/23 | 5 | 5 | 1
e42 | 530N02799A | f10 | tool_p3 | Function Setup | p3 | e42_p3 | Function Setup | 2025/12/24 | 2026/01/09 | 17 | 18 | 1.0588
e42 | 530N02799A | f10 | tool_p4 | Utility | p4 | e42_p4 | Utility | 2026/01/10 | 2026/02/16 | 38 | 16 | 0.42105
e43 | 530N02801A | f17 | tool_p1 | Module Setup | p1 | e43_p1 | Module Setup | 2025/07/25 | 2025/08/05 | 12 | 96 | 8
e43 | 530N02801A | f17 | tool_p2 | Hardware Setup | p2 | e43_p2 | Hardware Setup | 2025/08/06 | 2025/08/20 | 15 | 113 | 7.5333
e43 | 530N02801A | f17 | tool_p3 | Function Setup | p3 | e43_p3 | Function Setup | 2025/08/21 | 2025/08/29 | 9 | 29 | 3.2222
e43 | 530N02801A | f17 | tool_p4 | Utility | p4 | e43_p4 | Utility | 2025/08/30 | 2025/09/10 | 12 | 44 | 3.6667
e44 | 530N02802A | f18 | tool_p1 | Module Setup | p1 | e44_p1 | Module Setup | 2025/03/24 | 2025/04/10 | 18 | 44 | 2.4444
e44 | 530N02802A | f18 | tool_p2 | Hardware Setup | p2 | e44_p2 | Hardware Setup | 2025/04/11 | 2025/04/21 | 11 | 49 | 4.4545
e44 | 530N02802A | f18 | tool_p3 | Function Setup | p3 | e44_p3 | Function Setup | 2025/04/22 | 2025/04/28 | 7 | 42 | 6
e44 | 530N02802A | f18 | tool_p4 | Utility | p4 | e44_p4 | Utility | 2025/04/29 | 2025/08/02 | 96 | 97 | 1.0104
e45 | 530N02817A | f6 | tool_p1 | Module Setup | p1 | e45_p1 | Module Setup | 2025/05/19 | 2025/05/23 | 5 | 16 | 3.2
e45 | 530N02817A | f6 | tool_p2 | Hardware Setup | p2 | e45_p2 | Hardware Setup | 2025/05/24 | 2025/07/05 | 43 | 190 | 4.4186
e45 | 530N02817A | f6 | tool_p3 | Function Setup | p3 | e45_p3 | Function Setup | 2025/07/06 | 2025/07/25 | 20 | 37 | 1.85
e45 | 530N02817A | f6 | tool_p4 | Utility | p4 | e45_p4 | Utility | 2025/07/26 | 2025/07/26 | 1 | 1 | 1
e46 | 530N02818A | f19 | tool_p1 | Module Setup | p1 | e46_p1 | Module Setup | 2026/02/23 | 2026/03/05 | 11 | 66 | 6
e46 | 530N02818A | f19 | tool_p2 | Hardware Setup | p2 | e46_p2 | Hardware Setup | 2026/03/06 | 2026/03/19 | 14 | 106 | 7.5714
e46 | 530N02818A | f19 | tool_p3 | Function Setup | p3 | e46_p3 | Function Setup | 2026/03/20 | 2026/03/30 | 11 | 58 | 5.2727
e46 | 530N02818A | f19 | tool_p4 | Utility | p4 | e46_p4 | Utility | 2026/03/31 | 2026/03/31 | 1 | 2 | 2
e47 | 530N02819A | f20 | tool_p1 | Module Setup | p1 | e47_p1 | Module Setup | 2025/04/09 | 2025/05/22 | 44 | 65 | 1.4773
e47 | 530N02819A | f20 | tool_p2 | Hardware Setup | p2 | e47_p2 | Hardware Setup | 2025/05/23 | 2025/06/08 | 17 | 63 | 3.7059
e47 | 530N02819A | f20 | tool_p3 | Function Setup | p3 | e47_p3 | Function Setup | 2025/06/09 | 2025/06/15 | 7 | 13 | 1.8571
e47 | 530N02819A | f20 | tool_p4 | Utility | p4 | e47_p4 | Utility | 2025/06/16 | 2025/07/24 | 39 | 67 | 1.7179
e48 | 530N02822A | f18 | tool_p1 | Module Setup | p1 | e48_p1 | Module Setup | 2025/04/10 | 2025/05/09 | 30 | 53 | 1.7667
e48 | 530N02822A | f18 | tool_p2 | Hardware Setup | p2 | e48_p2 | Hardware Setup | 2025/05/10 | 2025/05/29 | 20 | 116 | 5.8
e48 | 530N02822A | f18 | tool_p3 | Function Setup | p3 | e48_p3 | Function Setup | 2025/05/30 | 2025/06/18 | 20 | 62 | 3.1
e48 | 530N02822A | f18 | tool_p4 | Utility | p4 | e48_p4 | Utility | 2025/06/19 | 2025/07/05 | 17 | 28 | 1.6471
e49 | 530N02824A | f4 | tool_p1 | Module Setup | p1 | e49_p1 | Module Setup | 2025/02/24 | 2025/03/05 | 10 | 39 | 3.9
e49 | 530N02824A | f4 | tool_p2 | Hardware Setup | p2 | e49_p2 | Hardware Setup | 2025/03/06 | 2025/03/17 | 12 | 48 | 4
e49 | 530N02824A | f4 | tool_p3 | Function Setup | p3 | e49_p3 | Function Setup | 2025/03/18 | 2025/03/27 | 10 | 20 | 2
e49 | 530N02824A | f4 | tool_p4 | Utility | p4 | e49_p4 | Utility | 2025/03/28 | 2025/04/10 | 14 | 16 | 1.1429
e50 | 530N02846A | f21 | tool_p1 | Module Setup | p1 | e50_p1 | Module Setup | 2025/03/24 | 2025/03/25 | 2 | 2 | 1
e50 | 530N02846A | f21 | tool_p2 | Hardware Setup | p2 | e50_p2 | Hardware Setup | 2025/03/26 | 2025/03/27 | 2 | 2 | 1
e50 | 530N02846A | f21 | tool_p3 | Function Setup | p3 | e50_p3 | Function Setup | 2025/03/28 | 2025/03/28 | 1 | 1 | 1
e50 | 530N02846A | f21 | tool_p4 | Utility | p4 | e50_p4 | Utility | 2025/03/29 | 2025/04/02 | 5 | 5 | 1
e51 | 530N02848A | f22 | tool_p1 | Module Setup | p1 | e51_p1 | Module Setup | 2025/07/17 | 2025/08/09 | 24 | 86 | 3.5833
e51 | 530N02848A | f22 | tool_p2 | Hardware Setup | p2 | e51_p2 | Hardware Setup | 2025/08/10 | 2025/08/30 | 21 | 118 | 5.619
e51 | 530N02848A | f22 | tool_p3 | Function Setup | p3 | e51_p3 | Function Setup | 2025/08/31 | 2025/09/08 | 9 | 26 | 2.8889
e51 | 530N02848A | f22 | tool_p4 | Utility | p4 | e51_p4 | Utility | 2025/09/09 | 2025/11/13 | 66 | 69 | 1.0455
e52 | 530N02849A | f17 | tool_p1 | Module Setup | p1 | e52_p1 | Module Setup | 2025/08/19 | 2025/09/18 | 31 | 114 | 3.6774
e52 | 530N02849A | f17 | tool_p2 | Hardware Setup | p2 | e52_p2 | Hardware Setup | 2025/09/19 | 2025/10/10 | 22 | 68 | 3.0909
e52 | 530N02849A | f17 | tool_p3 | Function Setup | p3 | e52_p3 | Function Setup | 2025/10/11 | 2025/10/22 | 12 | 32 | 2.6667
e52 | 530N02849A | f17 | tool_p4 | Utility | p4 | e52_p4 | Utility | 2025/10/23 | 2025/11/16 | 25 | 42 | 1.68
e53 | 530N02876A | f23 | tool_p1 | Module Setup | p1 | e53_p1 | Module Setup | 2025/12/30 | 2026/01/08 | 10 | 25 | 2.5
e53 | 530N02876A | f23 | tool_p2 | Hardware Setup | p2 | e53_p2 | Hardware Setup | 2026/01/09 | 2026/01/14 | 6 | 30 | 5
e53 | 530N02876A | f23 | tool_p3 | Function Setup | p3 | e53_p3 | Function Setup | 2026/01/15 | 2026/01/22 | 8 | 40 | 5
e53 | 530N02876A | f23 | tool_p4 | Utility | p4 | e53_p4 | Utility | 2026/01/23 | 2026/01/30 | 8 | 35 | 4.375
e54 | 530N02887A | f23 | tool_p1 | Module Setup | p1 | e54_p1 | Module Setup | 2025/11/14 | 2025/11/23 | 10 | 16 | 1.6
e54 | 530N02887A | f23 | tool_p2 | Hardware Setup | p2 | e54_p2 | Hardware Setup | 2025/11/24 | 2025/11/30 | 7 | 12 | 1.7143
e54 | 530N02887A | f23 | tool_p3 | Function Setup | p3 | e54_p3 | Function Setup | 2025/12/01 | 2025/12/03 | 3 | 3 | 1
e54 | 530N02887A | f23 | tool_p4 | Utility | p4 | e54_p4 | Utility | 2025/12/04 | 2025/12/10 | 7 | 7 | 1
e55 | 530N02888A | f23 | tool_p1 | Module Setup | p1 | e55_p1 | Module Setup | 2025/11/20 | 2025/11/28 | 9 | 18 | 2
e55 | 530N02888A | f23 | tool_p2 | Hardware Setup | p2 | e55_p2 | Hardware Setup | 2025/11/29 | 2025/12/02 | 4 | 8 | 2
e55 | 530N02888A | f23 | tool_p3 | Function Setup | p3 | e55_p3 | Function Setup | 2025/12/03 | 2025/12/09 | 7 | 14 | 2
e55 | 530N02888A | f23 | tool_p4 | Utility | p4 | e55_p4 | Utility | 2025/12/10 | 2025/12/16 | 7 | 13 | 1.8571
e56 | 530N02914A | f18 | tool_p1 | Module Setup | p1 | e56_p1 | Module Setup | 2025/08/05 | 2025/09/11 | 38 | 104 | 2.7368
e56 | 530N02914A | f18 | tool_p2 | Hardware Setup | p2 | e56_p2 | Hardware Setup | 2025/09/12 | 2025/10/17 | 36 | 117 | 3.25
e56 | 530N02914A | f18 | tool_p3 | Function Setup | p3 | e56_p3 | Function Setup | 2025/10/18 | 2025/11/20 | 34 | 29 | 0.85294
e56 | 530N02914A | f18 | tool_p4 | Utility | p4 | e56_p4 | Utility | 2025/11/21 | 2025/12/21 | 31 | 25 | 0.80645
e57 | 530N02920A | f24 | tool_p1 | Module Setup | p1 | e57_p1 | Module Setup | 2025/06/12 | 2025/06/19 | 8 | 45 | 5.625
e57 | 530N02920A | f24 | tool_p2 | Hardware Setup | p2 | e57_p2 | Hardware Setup | 2025/06/20 | 2025/07/12 | 23 | 91 | 3.9565
e57 | 530N02920A | f24 | tool_p3 | Function Setup | p3 | e57_p3 | Function Setup | 2025/07/13 | 2025/07/25 | 13 | 34 | 2.6154
e57 | 530N02920A | f24 | tool_p4 | Utility | p4 | e57_p4 | Utility | 2025/07/26 | 2025/08/22 | 28 | 48 | 1.7143
e58 | 530N02921A | f24 | tool_p1 | Module Setup | p1 | e58_p1 | Module Setup | 2025/06/13 | 2025/06/22 | 10 | 25 | 2.5
e58 | 530N02921A | f24 | tool_p2 | Hardware Setup | p2 | e58_p2 | Hardware Setup | 2025/06/23 | 2025/07/13 | 21 | 86 | 4.0952
e58 | 530N02921A | f24 | tool_p3 | Function Setup | p3 | e58_p3 | Function Setup | 2025/07/14 | 2025/07/29 | 16 | 49 | 3.0625
e58 | 530N02921A | f24 | tool_p4 | Utility | p4 | e58_p4 | Utility | 2025/07/30 | 2025/08/22 | 24 | 47 | 1.9583
e59 | 530N02923A | f16 | tool_p1 | Module Setup | p1 | e59_p1 | Module Setup | 2025/04/15 | 2025/05/17 | 33 | 144 | 4.3636
e59 | 530N02923A | f16 | tool_p2 | Hardware Setup | p2 | e59_p2 | Hardware Setup | 2025/05/18 | 2025/06/25 | 39 | 223 | 5.7179
e59 | 530N02923A | f16 | tool_p3 | Function Setup | p3 | e59_p3 | Function Setup | 2025/06/26 | 2025/07/19 | 24 | 58 | 2.4167
e59 | 530N02923A | f16 | tool_p4 | Utility | p4 | e59_p4 | Utility | 2025/07/20 | 2025/08/19 | 31 | 164 | 5.2903
e60 | 530N02924A | f16 | tool_p1 | Module Setup | p1 | e60_p1 | Module Setup | 2025/05/13 | 2025/06/13 | 32 | 118 | 3.6875
e60 | 530N02924A | f16 | tool_p2 | Hardware Setup | p2 | e60_p2 | Hardware Setup | 2025/06/14 | 2025/07/15 | 32 | 238 | 7.4375
e60 | 530N02924A | f16 | tool_p3 | Function Setup | p3 | e60_p3 | Function Setup | 2025/07/16 | 2025/08/04 | 20 | 54 | 2.7
e60 | 530N02924A | f16 | tool_p4 | Utility | p4 | e60_p4 | Utility | 2025/08/05 | 2025/08/30 | 26 | 51 | 1.9615
e61 | 530N02930A | f16 | tool_p1 | Module Setup | p1 | e61_p1 | Module Setup | 2025/11/03 | 2025/11/03 | 1 | 1 | 1
e61 | 530N02930A | f16 | tool_p2 | Hardware Setup | p2 | e61_p2 | Hardware Setup | 2025/11/04 | 2025/11/05 | 2 | 2 | 1
e61 | 530N02930A | f16 | tool_p3 | Function Setup | p3 | e61_p3 | Function Setup | 2025/11/06 | 2025/11/06 | 1 | 1 | 1
e61 | 530N02930A | f16 | tool_p4 | Utility | p4 | e61_p4 | Utility | 2025/11/07 | 2025/11/07 | 1 | 1 | 1
e62 | 530N02934A | f16 | tool_p1 | Module Setup | p1 | e62_p1 | Module Setup | 2025/07/05 | 2025/07/08 | 4 | 4 | 1
e62 | 530N02934A | f16 | tool_p2 | Hardware Setup | p2 | e62_p2 | Hardware Setup | 2025/07/09 | 2025/07/15 | 7 | 7 | 1
e62 | 530N02934A | f16 | tool_p3 | Function Setup | p3 | e62_p3 | Function Setup | 2025/07/16 | 2025/07/20 | 5 | 5 | 1
e62 | 530N02934A | f16 | tool_p4 | Utility | p4 | e62_p4 | Utility | 2025/07/21 | 2025/07/26 | 6 | 6 | 1
e63 | 530N02959A | f25 | tool_p1 | Module Setup | p1 | e63_p1 | Module Setup | 2025/11/21 | 2025/11/28 | 8 | 8 | 1
e63 | 530N02959A | f25 | tool_p2 | Hardware Setup | p2 | e63_p2 | Hardware Setup | 2025/11/29 | 2025/12/04 | 6 | 6 | 1
e63 | 530N02959A | f25 | tool_p3 | Function Setup | p3 | e63_p3 | Function Setup | 2025/12/05 | 2025/12/07 | 3 | 3 | 1
e63 | 530N02959A | f25 | tool_p4 | Utility | p4 | e63_p4 | Utility | 2025/12/08 | 2025/12/13 | 6 | 6 | 1
e64 | 530N02971A | f14 | tool_p1 | Module Setup | p1 | e64_p1 | Module Setup | 2025/09/19 | 2025/09/21 | 3 | 6 | 2
e64 | 530N02971A | f14 | tool_p2 | Hardware Setup | p2 | e64_p2 | Hardware Setup | 2025/09/22 | 2025/10/20 | 29 | 106 | 3.6552
e64 | 530N02971A | f14 | tool_p3 | Function Setup | p3 | e64_p3 | Function Setup | 2025/10/21 | 2025/11/30 | 41 | 35 | 0.85366
e64 | 530N02971A | f14 | tool_p4 | Utility | p4 | e64_p4 | Utility | 2025/12/01 | 2025/12/25 | 25 | 24 | 0.96
e65 | 530N03002A | f26 | tool_p1 | Module Setup | p1 | e65_p1 | Module Setup | 2025/10/30 | 2025/12/02 | 34 | 112 | 3.2941
e65 | 530N03002A | f26 | tool_p2 | Hardware Setup | p2 | e65_p2 | Hardware Setup | 2025/12/03 | 2025/12/18 | 16 | 67 | 4.1875
e65 | 530N03002A | f26 | tool_p3 | Function Setup | p3 | e65_p3 | Function Setup | 2025/12/19 | 2026/01/03 | 16 | 34 | 2.125
e65 | 530N03002A | f26 | tool_p4 | Utility | p4 | e65_p4 | Utility | 2026/01/04 | 2026/01/16 | 13 | 26 | 2
e66 | 530N03014A | f14 | tool_p1 | Module Setup | p1 | e66_p1 | Module Setup | 2025/11/18 | 2025/11/22 | 5 | 5 | 1
e66 | 530N03014A | f14 | tool_p2 | Hardware Setup | p2 | e66_p2 | Hardware Setup | 2025/11/23 | 2026/01/14 | 53 | 34 | 0.64151
e66 | 530N03014A | f14 | tool_p3 | Function Setup | p3 | e66_p3 | Function Setup | 2026/01/15 | 2026/02/04 | 21 | 21 | 1
e66 | 530N03014A | f14 | tool_p4 | Utility | p4 | e66_p4 | Utility | 2026/02/05 | 2026/03/16 | 40 | 28 | 0.7
e67 | 530N03065A | f27 | tool_p1 | Module Setup | p1 | e67_p1 | Module Setup | 2025/11/20 | 2026/01/25 | 67 | 96 | 1.4328
e67 | 530N03065A | f27 | tool_p2 | Hardware Setup | p2 | e67_p2 | Hardware Setup | 2026/01/26 | 2026/02/13 | 19 | 96 | 5.0526
e67 | 530N03065A | f27 | tool_p3 | Function Setup | p3 | e67_p3 | Function Setup | 2026/02/14 | 2026/03/04 | 19 | 82 | 4.3158
e67 | 530N03065A | f27 | tool_p4 | Utility | p4 | e67_p4 | Utility | 2026/03/05 | 2026/03/21 | 17 | 29 | 1.7059
e68 | 530N03073A | f28 | tool_p1 | Module Setup | p1 | e68_p1 | Module Setup | 2025/11/11 | 2025/11/28 | 18 | 132 | 7.3333
e68 | 530N03073A | f28 | tool_p2 | Hardware Setup | p2 | e68_p2 | Hardware Setup | 2025/11/29 | 2025/12/20 | 22 | 187 | 8.5
e68 | 530N03073A | f28 | tool_p3 | Function Setup | p3 | e68_p3 | Function Setup | 2025/12/21 | 2026/01/05 | 16 | 48 | 3
e68 | 530N03073A | f28 | tool_p4 | Utility | p4 | e68_p4 | Utility | 2026/01/06 | 2026/01/13 | 8 | 8 | 1
e69 | 530N03074A | f28 | tool_p1 | Module Setup | p1 | e69_p1 | Module Setup | 2025/11/06 | 2025/11/24 | 19 | 122 | 6.4211
e69 | 530N03074A | f28 | tool_p2 | Hardware Setup | p2 | e69_p2 | Hardware Setup | 2025/11/25 | 2025/12/18 | 24 | 170 | 7.0833
e69 | 530N03074A | f28 | tool_p3 | Function Setup | p3 | e69_p3 | Function Setup | 2025/12/19 | 2026/01/04 | 17 | 65 | 3.8235
e69 | 530N03074A | f28 | tool_p4 | Utility | p4 | e69_p4 | Utility | 2026/01/05 | 2026/01/13 | 9 | 9 | 1
e70 | 530N03075A | f14 | tool_p1 | Module Setup | p1 | e70_p1 | Module Setup | 2025/12/04 | 2025/12/07 | 4 | 4 | 1
e70 | 530N03075A | f14 | tool_p2 | Hardware Setup | p2 | e70_p2 | Hardware Setup | 2025/12/08 | 2025/12/14 | 7 | 14 | 2
e70 | 530N03075A | f14 | tool_p3 | Function Setup | p3 | e70_p3 | Function Setup | 2025/12/15 | 2025/12/19 | 5 | 10 | 2
e70 | 530N03075A | f14 | tool_p4 | Utility | p4 | e70_p4 | Utility | 2025/12/20 | 2025/12/25 | 6 | 12 | 2
e71 | 530N03081A | f14 | tool_p1 | Module Setup | p1 | e71_p1 | Module Setup | 2025/10/06 | 2025/10/06 | 1 | 2 | 2
e71 | 530N03081A | f14 | tool_p2 | Hardware Setup | p2 | e71_p2 | Hardware Setup | 2025/10/07 | 2025/11/12 | 37 | 48 | 1.2973
e71 | 530N03081A | f14 | tool_p3 | Function Setup | p3 | e71_p3 | Function Setup | 2025/11/13 | 2025/11/29 | 17 | 30 | 1.7647
e71 | 530N03081A | f14 | tool_p4 | Utility | p4 | e71_p4 | Utility | 2025/11/30 | 2026/01/19 | 51 | 81 | 1.5882
e72 | 530N03082A | f29 | tool_p1 | Module Setup | p1 | e72_p1 | Module Setup | 2025/10/24 | 2025/12/07 | 45 | 190 | 4.2222
e72 | 530N03082A | f29 | tool_p2 | Hardware Setup | p2 | e72_p2 | Hardware Setup | 2025/12/08 | 2026/01/06 | 30 | 119 | 3.9667
e72 | 530N03082A | f29 | tool_p3 | Function Setup | p3 | e72_p3 | Function Setup | 2026/01/07 | 2026/01/31 | 25 | 133 | 5.32
e72 | 530N03082A | f29 | tool_p4 | Utility | p4 | e72_p4 | Utility | 2026/02/01 | 2026/03/13 | 41 | 82 | 2
e73 | 530N03107A | f30 | tool_p1 | Module Setup | p1 | e73_p1 | Module Setup | 2025/09/18 | 2025/10/21 | 34 | 326 | 9.5882
e73 | 530N03107A | f30 | tool_p2 | Hardware Setup | p2 | e73_p2 | Hardware Setup | 2025/10/22 | 2025/11/14 | 24 | 66 | 2.75
e73 | 530N03107A | f30 | tool_p3 | Function Setup | p3 | e73_p3 | Function Setup | 2025/11/15 | 2025/12/07 | 23 | 23 | 1
e73 | 530N03107A | f30 | tool_p4 | Utility | p4 | e73_p4 | Utility | 2025/12/08 | 2025/12/27 | 20 | 20 | 1
e74 | 530N03156A | f31 | tool_p1 | Module Setup | p1 | e74_p1 | Module Setup | 2026/01/14 | 2026/01/31 | 18 | 106 | 5.8889
e74 | 530N03156A | f31 | tool_p2 | Hardware Setup | p2 | e74_p2 | Hardware Setup | 2026/02/01 | 2026/02/13 | 13 | 67 | 5.1538
e74 | 530N03156A | f31 | tool_p3 | Function Setup | p3 | e74_p3 | Function Setup | 2026/02/14 | 2026/03/01 | 16 | 77 | 4.8125
e74 | 530N03156A | f31 | tool_p4 | Utility | p4 | e74_p4 | Utility | 2026/03/02 | 2026/03/27 | 26 | 88 | 3.3846
e75 | 830300168A | f32 | tool_p1 | Module Setup | p1 | e75_p1 | Module Setup | 2025/01/07 | 2025/01/18 | 12 | 42 | 3.5
e75 | 830300168A | f32 | tool_p2 | Hardware Setup | p2 | e75_p2 | Hardware Setup | 2025/01/19 | 2025/02/17 | 30 | 111 | 3.7
e75 | 830300168A | f32 | tool_p3 | Function Setup | p3 | e75_p3 | Function Setup | 2025/02/18 | 2025/02/26 | 9 | 29 | 3.2222
e75 | 830300168A | f32 | tool_p4 | Utility | p4 | e75_p4 | Utility | 2025/02/27 | 2025/07/25 | 149 | 280 | 1.8792
e76 | 830300171A | f22 | tool_p1 | Module Setup | p1 | e76_p1 | Module Setup | 2025/01/06 | 2025/01/17 | 12 | 57 | 4.75
e76 | 830300171A | f22 | tool_p2 | Hardware Setup | p2 | e76_p2 | Hardware Setup | 2025/01/18 | 2025/01/26 | 9 | 43 | 4.7778
e76 | 830300171A | f22 | tool_p3 | Function Setup | p3 | e76_p3 | Function Setup | 2025/01/27 | 2025/02/03 | 8 | 16 | 2
e76 | 830300171A | f22 | tool_p4 | Utility | p4 | e76_p4 | Utility | 2025/02/04 | 2025/02/14 | 11 | 15 | 1.3636
e77 | 830300176A | f17 | tool_p1 | Module Setup | p1 | e77_p1 | Module Setup | 2025/01/01 | 2025/01/01 | 1 | 1 | 1
e77 | 830300176A | f17 | tool_p2 | Hardware Setup | p2 | e77_p2 | Hardware Setup | 2025/01/02 | 2025/01/02 | 1 | 1 | 1
e77 | 830300176A | f17 | tool_p3 | Function Setup | p3 | e77_p3 | Function Setup | 2025/01/03 | 2025/01/04 | 2 | 2 | 1
e77 | 830300176A | f17 | tool_p4 | Utility | p4 | e77_p4 | Utility | 2025/01/05 | 2025/01/06 | 2 | 2 | 1
e78 | 830300178A | f33 | tool_p1 | Module Setup | p1 | e78_p1 | Module Setup | 2025/02/03 | 2025/02/16 | 14 | 74 | 5.2857
e78 | 830300178A | f33 | tool_p2 | Hardware Setup | p2 | e78_p2 | Hardware Setup | 2025/02/17 | 2025/02/26 | 10 | 64 | 6.4
e78 | 830300178A | f33 | tool_p3 | Function Setup | p3 | e78_p3 | Function Setup | 2025/02/27 | 2025/03/08 | 10 | 30 | 3
e78 | 830300178A | f33 | tool_p4 | Utility | p4 | e78_p4 | Utility | 2025/03/09 | 2025/03/22 | 14 | 34 | 2.4286
e79 | 830300179A | f22 | tool_p1 | Module Setup | p1 | e79_p1 | Module Setup | 2025/02/04 | 2025/03/13 | 38 | 295 | 7.7632
e79 | 830300179A | f22 | tool_p2 | Hardware Setup | p2 | e79_p2 | Hardware Setup | 2025/03/14 | 2025/04/06 | 24 | 211 | 8.7917
e79 | 830300179A | f22 | tool_p3 | Function Setup | p3 | e79_p3 | Function Setup | 2025/04/07 | 2025/04/29 | 23 | 79 | 3.4348
e79 | 830300179A | f22 | tool_p4 | Utility | p4 | e79_p4 | Utility | 2025/04/30 | 2025/05/31 | 32 | 36 | 1.125
e80 | 830300180A | f17 | tool_p1 | Module Setup | p1 | e80_p1 | Module Setup | 2025/02/14 | 2025/03/12 | 27 | 112 | 4.1481
e80 | 830300180A | f17 | tool_p2 | Hardware Setup | p2 | e80_p2 | Hardware Setup | 2025/03/13 | 2025/04/01 | 20 | 47 | 2.35
e80 | 830300180A | f17 | tool_p3 | Function Setup | p3 | e80_p3 | Function Setup | 2025/04/02 | 2025/04/20 | 19 | 19 | 1
e80 | 830300180A | f17 | tool_p4 | Utility | p4 | e80_p4 | Utility | 2025/04/21 | 2025/05/17 | 27 | 27 | 1
e81 | 830300182A | f17 | tool_p1 | Module Setup | p1 | e81_p1 | Module Setup | 2025/03/07 | 2025/03/24 | 18 | 93 | 5.1667
e81 | 830300182A | f17 | tool_p2 | Hardware Setup | p2 | e81_p2 | Hardware Setup | 2025/03/25 | 2025/04/06 | 13 | 41 | 3.1538
e81 | 830300182A | f17 | tool_p3 | Function Setup | p3 | e81_p3 | Function Setup | 2025/04/07 | 2025/04/18 | 12 | 33 | 2.75
e81 | 830300182A | f17 | tool_p4 | Utility | p4 | e81_p4 | Utility | 2025/04/19 | 2025/05/06 | 18 | 23 | 1.2778
e82 | 830300183A | f31 | tool_p1 | Module Setup | p1 | e82_p1 | Module Setup | 2025/01/11 | 2025/01/21 | 11 | 69 | 6.2727
e82 | 830300183A | f31 | tool_p2 | Hardware Setup | p2 | e82_p2 | Hardware Setup | 2025/01/22 | 2025/02/10 | 20 | 121 | 6.05
e82 | 830300183A | f31 | tool_p3 | Function Setup | p3 | e82_p3 | Function Setup | 2025/02/11 | 2025/03/06 | 24 | 83 | 3.4583
e82 | 830300183A | f31 | tool_p4 | Utility | p4 | e82_p4 | Utility | 2025/03/07 | 2025/03/21 | 15 | 31 | 2.0667
e83 | 830300184A | f17 | tool_p1 | Module Setup | p1 | e83_p1 | Module Setup | 2025/03/14 | 2025/04/03 | 21 | 87 | 4.1429
e83 | 830300184A | f17 | tool_p2 | Hardware Setup | p2 | e83_p2 | Hardware Setup | 2025/04/04 | 2025/04/18 | 15 | 66 | 4.4
e83 | 830300184A | f17 | tool_p3 | Function Setup | p3 | e83_p3 | Function Setup | 2025/04/19 | 2025/05/25 | 37 | 16 | 0.43243
e83 | 830300184A | f17 | tool_p4 | Utility | p4 | e83_p4 | Utility | 2025/05/26 | 2025/06/14 | 20 | 20 | 1
e84 | 830300185A | f17 | tool_p1 | Module Setup | p1 | e84_p1 | Module Setup | 2025/03/23 | 2025/04/26 | 35 | 70 | 2
e84 | 830300185A | f17 | tool_p2 | Hardware Setup | p2 | e84_p2 | Hardware Setup | 2025/04/27 | 2025/05/14 | 18 | 74 | 4.1111
e84 | 830300185A | f17 | tool_p3 | Function Setup | p3 | e84_p3 | Function Setup | 2025/05/15 | 2025/06/03 | 20 | 27 | 1.35
e84 | 830300185A | f17 | tool_p4 | Utility | p4 | e84_p4 | Utility | 2025/06/04 | 2025/06/27 | 24 | 48 | 2
e85 | 830300186A | f17 | tool_p1 | Module Setup | p1 | e85_p1 | Module Setup | 2025/05/21 | 2025/06/08 | 19 | 19 | 1
e85 | 830300186A | f17 | tool_p2 | Hardware Setup | p2 | e85_p2 | Hardware Setup | 2025/06/09 | 2025/06/22 | 14 | 14 | 1
e85 | 830300186A | f17 | tool_p3 | Function Setup | p3 | e85_p3 | Function Setup | 2025/06/23 | 2025/07/06 | 14 | 14 | 1
e85 | 830300186A | f17 | tool_p4 | Utility | p4 | e85_p4 | Utility | 2025/07/07 | 2025/07/25 | 19 | 19 | 1
e86 | 830300188A | f34 | tool_p1 | Module Setup | p1 | e86_p1 | Module Setup | 2025/06/30 | 2025/08/11 | 43 | 270 | 6.2791
e86 | 830300188A | f34 | tool_p2 | Hardware Setup | p2 | e86_p2 | Hardware Setup | 2025/08/12 | 2025/08/30 | 19 | 50 | 2.6316
e86 | 830300188A | f34 | tool_p3 | Function Setup | p3 | e86_p3 | Function Setup | 2025/08/31 | 2025/09/15 | 16 | 32 | 2
e86 | 830300188A | f34 | tool_p4 | Utility | p4 | e86_p4 | Utility | 2025/09/16 | 2025/09/30 | 15 | 29 | 1.9333
e87 | 830300189A | f22 | tool_p1 | Module Setup | p1 | e87_p1 | Module Setup | 2025/08/25 | 2025/08/26 | 2 | 24 | 12
e87 | 830300189A | f22 | tool_p2 | Hardware Setup | p2 | e87_p2 | Hardware Setup | 2025/08/27 | 2025/08/28 | 2 | 24 | 12
e87 | 830300189A | f22 | tool_p3 | Function Setup | p3 | e87_p3 | Function Setup | 2025/08/29 | 2025/08/29 | 1 | 12 | 12
e87 | 830300189A | f22 | tool_p4 | Utility | p4 | e87_p4 | Utility | 2025/08/30 | 2025/08/31 | 2 | 24 | 12
e88 | 830300192A | f35 | tool_p1 | Module Setup | p1 | e88_p1 | Module Setup | 2025/05/14 | 2025/05/17 | 4 | 8 | 2
e88 | 830300192A | f35 | tool_p2 | Hardware Setup | p2 | e88_p2 | Hardware Setup | 2025/05/18 | 2025/05/20 | 3 | 6 | 2
e88 | 830300192A | f35 | tool_p3 | Function Setup | p3 | e88_p3 | Function Setup | 2025/05/21 | 2025/05/22 | 2 | 4 | 2
e88 | 830300192A | f35 | tool_p4 | Utility | p4 | e88_p4 | Utility | 2025/05/23 | 2025/05/26 | 4 | 7 | 1.75
e89 | 830300193A | f31 | tool_p1 | Module Setup | p1 | e89_p1 | Module Setup | 2025/03/24 | 2025/04/07 | 15 | 60 | 4
e89 | 830300193A | f31 | tool_p2 | Hardware Setup | p2 | e89_p2 | Hardware Setup | 2025/04/08 | 2025/04/22 | 15 | 101 | 6.7333
e89 | 830300193A | f31 | tool_p3 | Function Setup | p3 | e89_p3 | Function Setup | 2025/04/23 | 2025/05/03 | 11 | 72 | 6.5455
e89 | 830300193A | f31 | tool_p4 | Utility | p4 | e89_p4 | Utility | 2025/05/04 | 2025/05/29 | 26 | 71 | 2.7308
e90 | 830300198A | f31 | tool_p1 | Module Setup | p1 | e90_p1 | Module Setup | 2025/07/05 | 2025/07/15 | 11 | 78 | 7.0909
e90 | 830300198A | f31 | tool_p2 | Hardware Setup | p2 | e90_p2 | Hardware Setup | 2025/07/16 | 2025/07/26 | 11 | 55 | 5
e90 | 830300198A | f31 | tool_p3 | Function Setup | p3 | e90_p3 | Function Setup | 2025/07/27 | 2025/08/12 | 17 | 77 | 4.5294
e90 | 830300198A | f31 | tool_p4 | Utility | p4 | e90_p4 | Utility | 2025/08/13 | 2025/08/30 | 18 | 36 | 2
e91 | 830300201A | f17 | tool_p1 | Module Setup | p1 | e91_p1 | Module Setup | 2025/07/17 | 2025/08/03 | 18 | 90 | 5
e91 | 830300201A | f17 | tool_p2 | Hardware Setup | p2 | e91_p2 | Hardware Setup | 2025/08/04 | 2025/08/16 | 13 | 54 | 4.1538
e91 | 830300201A | f17 | tool_p3 | Function Setup | p3 | e91_p3 | Function Setup | 2025/08/17 | 2025/08/29 | 13 | 26 | 2
e91 | 830300201A | f17 | tool_p4 | Utility | p4 | e91_p4 | Utility | 2025/08/30 | 2025/09/20 | 22 | 22 | 1
e92 | 830300202A | f30 | tool_p1 | Module Setup | p1 | e92_p1 | Module Setup | 2025/09/01 | 2025/09/28 | 28 | 45 | 1.6071
e92 | 830300202A | f30 | tool_p2 | Hardware Setup | p2 | e92_p2 | Hardware Setup | 2025/09/29 | 2025/10/23 | 25 | 11 | 0.44
e92 | 830300202A | f30 | tool_p3 | Function Setup | p3 | e92_p3 | Function Setup | 2025/10/24 | 2025/11/24 | 32 | 32 | 1
e92 | 830300202A | f30 | tool_p4 | Utility | p4 | e92_p4 | Utility | 2025/11/25 | 2025/12/24 | 30 | 30 | 1
e93 | 830300204A | f31 | tool_p1 | Module Setup | p1 | e93_p1 | Module Setup | 2025/07/11 | 2025/08/02 | 23 | 156 | 6.7826
e93 | 830300204A | f31 | tool_p2 | Hardware Setup | p2 | e93_p2 | Hardware Setup | 2025/08/03 | 2025/08/29 | 27 | 135 | 5
e93 | 830300204A | f31 | tool_p3 | Function Setup | p3 | e93_p3 | Function Setup | 2025/08/30 | 2025/09/19 | 21 | 42 | 2
e93 | 830300204A | f31 | tool_p4 | Utility | p4 | e93_p4 | Utility | 2025/09/20 | 2025/10/25 | 36 | 44 | 1.2222
e94 | 830300205A | f31 | tool_p1 | Module Setup | p1 | e94_p1 | Module Setup | 2025/07/12 | 2025/08/18 | 38 | 204 | 5.3684
e94 | 830300205A | f31 | tool_p2 | Hardware Setup | p2 | e94_p2 | Hardware Setup | 2025/08/19 | 2025/09/28 | 41 | 145 | 3.5366
e94 | 830300205A | f31 | tool_p3 | Function Setup | p3 | e94_p3 | Function Setup | 2025/09/29 | 2025/10/29 | 31 | 60 | 1.9355
e94 | 830300205A | f31 | tool_p4 | Utility | p4 | e94_p4 | Utility | 2025/10/30 | 2025/11/28 | 30 | 66 | 2.2
e95 | 830400201A | f13 | tool_p1 | Module Setup | p1 | e95_p1 | Module Setup | 2025/01/01 | 2025/01/12 | 12 | 65 | 5.4167
e95 | 830400201A | f13 | tool_p2 | Hardware Setup | p2 | e95_p2 | Hardware Setup | 2025/01/13 | 2025/01/26 | 14 | 34 | 2.4286
e95 | 830400201A | f13 | tool_p3 | Function Setup | p3 | e95_p3 | Function Setup | 2025/01/27 | 2025/02/03 | 8 | 16 | 2
e95 | 830400201A | f13 | tool_p4 | Utility | p4 | e95_p4 | Utility | 2025/02/04 | 2025/02/14 | 11 | 16 | 1.4545
e96 | 830400202A | f36 | tool_p1 | Module Setup | p1 | e96_p1 | Module Setup | 2025/01/01 | 2025/01/02 | 2 | 4 | 2
e96 | 830400202A | f36 | tool_p2 | Hardware Setup | p2 | e96_p2 | Hardware Setup | 2025/01/03 | 2025/01/03 | 1 | 2 | 2
e96 | 830400202A | f36 | tool_p3 | Function Setup | p3 | e96_p3 | Function Setup | 2025/01/04 | 2025/01/04 | 1 | 2 | 2
e96 | 830400202A | f36 | tool_p4 | Utility | p4 | e96_p4 | Utility | 2025/01/05 | 2025/01/05 | 1 | 2 | 2
e97 | 830400204A | f14 | tool_p1 | Module Setup | p1 | e97_p1 | Module Setup | 2025/01/03 | 2025/02/03 | 32 | 143 | 4.4688
e97 | 830400204A | f14 | tool_p2 | Hardware Setup | p2 | e97_p2 | Hardware Setup | 2025/02/04 | 2025/03/06 | 31 | 185 | 5.9677
e97 | 830400204A | f14 | tool_p3 | Function Setup | p3 | e97_p3 | Function Setup | 2025/03/07 | 2025/03/25 | 19 | 100 | 5.2632
e97 | 830400204A | f14 | tool_p4 | Utility | p4 | e97_p4 | Utility | 2025/03/26 | 2025/04/19 | 25 | 63 | 2.52
e98 | 830400211A | f15 | tool_p1 | Module Setup | p1 | e98_p1 | Module Setup | 2025/04/07 | 2025/04/25 | 19 | 19 | 1
e98 | 830400211A | f15 | tool_p2 | Hardware Setup | p2 | e98_p2 | Hardware Setup | 2025/04/26 | 2025/05/14 | 19 | 23 | 1.2105
e98 | 830400211A | f15 | tool_p3 | Function Setup | p3 | e98_p3 | Function Setup | 2025/05/15 | 2025/05/25 | 11 | 18 | 1.6364
e98 | 830400211A | f15 | tool_p4 | Utility | p4 | e98_p4 | Utility | 2025/05/26 | 2025/06/09 | 15 | 15 | 1
e99 | 830400225A | f37 | tool_p1 | Module Setup | p1 | e99_p1 | Module Setup | 2025/10/21 | 2025/11/14 | 25 | 145 | 5.8
e99 | 830400225A | f37 | tool_p2 | Hardware Setup | p2 | e99_p2 | Hardware Setup | 2025/11/15 | 2025/12/10 | 26 | 143 | 5.5
e99 | 830400225A | f37 | tool_p3 | Function Setup | p3 | e99_p3 | Function Setup | 2025/12/11 | 2025/12/28 | 18 | 35 | 1.9444
e99 | 830400225A | f37 | tool_p4 | Utility | p4 | e99_p4 | Utility | 2025/12/29 | 2026/01/17 | 20 | 20 | 1
e100 | 830400228A | f23 | tool_p1 | Module Setup | p1 | e100_p1 | Module Setup | 2026/01/04 | 2026/01/07 | 4 | 4 | 1
e100 | 830400228A | f23 | tool_p2 | Hardware Setup | p2 | e100_p2 | Hardware Setup | 2026/01/08 | 2026/01/11 | 4 | 4 | 1
e100 | 830400228A | f23 | tool_p3 | Function Setup | p3 | e100_p3 | Function Setup | 2026/01/12 | 2026/01/14 | 3 | 3 | 1
e100 | 830400228A | f23 | tool_p4 | Utility | p4 | e100_p4 | Utility | 2026/01/15 | 2026/01/17 | 3 | 3 | 1
e101 | 830400232A | f23 | tool_p1 | Module Setup | p1 | e101_p1 | Module Setup | 2025/09/16 | 2025/10/14 | 29 | 23 | 0.7931
e101 | 830400232A | f23 | tool_p2 | Hardware Setup | p2 | e101_p2 | Hardware Setup | 2025/10/15 | 2025/11/06 | 23 | 38 | 1.6522
e101 | 830400232A | f23 | tool_p3 | Function Setup | p3 | e101_p3 | Function Setup | 2025/11/07 | 2025/11/20 | 14 | 26 | 1.8571
e101 | 830400232A | f23 | tool_p4 | Utility | p4 | e101_p4 | Utility | 2025/11/21 | 2025/12/08 | 18 | 18 | 1
e102 | 830C00003A | f10 | tool_p1 | Module Setup | p1 | e102_p1 | Module Setup | 2025/03/02 | 2025/04/04 | 34 | 115 | 3.3824
e102 | 830C00003A | f10 | tool_p2 | Hardware Setup | p2 | e102_p2 | Hardware Setup | 2025/04/05 | 2025/05/24 | 50 | 75 | 1.5
e102 | 830C00003A | f10 | tool_p3 | Function Setup | p3 | e102_p3 | Function Setup | 2025/05/25 | 2025/07/01 | 38 | 96 | 2.5263
e102 | 830C00003A | f10 | tool_p4 | Utility | p4 | e102_p4 | Utility | 2025/07/02 | 2025/07/30 | 29 | 73 | 2.5172
e103 | 830C00004A | f10 | tool_p1 | Module Setup | p1 | e103_p1 | Module Setup | 2025/01/05 | 2025/02/16 | 43 | 182 | 4.2326
e103 | 830C00004A | f10 | tool_p2 | Hardware Setup | p2 | e103_p2 | Hardware Setup | 2025/02/17 | 2025/02/25 | 9 | 11 | 1.2222
e103 | 830C00004A | f10 | tool_p3 | Function Setup | p3 | e103_p3 | Function Setup | 2025/02/26 | 2025/05/01 | 65 | 128 | 1.9692
e103 | 830C00004A | f10 | tool_p4 | Utility | p4 | e103_p4 | Utility | 2025/05/02 | 2025/06/02 | 32 | 54 | 1.6875
e104 | 830C00011A | f38 | tool_p1 | Module Setup | p1 | e104_p1 | Module Setup | 2026/03/16 | 2026/03/20 | 5 | 25 | 5
e104 | 830C00011A | f38 | tool_p2 | Hardware Setup | p2 | e104_p2 | Hardware Setup | 2026/03/21 | 2026/03/24 | 4 | 20 | 5
e104 | 830C00011A | f38 | tool_p3 | Function Setup | p3 | e104_p3 | Function Setup | 2026/03/25 | 2026/03/26 | 2 | 10 | 5
e104 | 830C00011A | f38 | tool_p4 | Utility | p4 | e104_p4 | Utility | 2026/03/27 | 2026/03/31 | 5 | 25 | 5
e105 | 830D00008A | f39 | tool_p1 | Module Setup | p1 | e105_p1 | Module Setup | 2025/01/06 | 2025/01/13 | 8 | 16 | 2
e105 | 830D00008A | f39 | tool_p2 | Hardware Setup | p2 | e105_p2 | Hardware Setup | 2025/01/14 | 2025/02/03 | 21 | 42 | 2
e105 | 830D00008A | f39 | tool_p3 | Function Setup | p3 | e105_p3 | Function Setup | 2025/02/04 | 2025/02/04 | 1 | 2 | 2
e105 | 830D00008A | f39 | tool_p4 | Utility | p4 | e105_p4 | Utility | 2025/02/05 | 2025/02/09 | 5 | 10 | 2
e106 | 830D00009A | f32 | tool_p1 | Module Setup | p1 | e106_p1 | Module Setup | 2025/01/08 | 2025/01/09 | 2 | 4 | 2
e106 | 830D00009A | f32 | tool_p2 | Hardware Setup | p2 | e106_p2 | Hardware Setup | 2025/01/10 | 2025/01/12 | 3 | 6 | 2
e106 | 830D00009A | f32 | tool_p3 | Function Setup | p3 | e106_p3 | Function Setup | 2025/01/13 | 2025/01/14 | 2 | 4 | 2
e106 | 830D00009A | f32 | tool_p4 | Utility | p4 | e106_p4 | Utility | 2025/01/15 | 2025/02/07 | 24 | 43 | 1.7917
e107 | 830D00010A | f39 | tool_p1 | Module Setup | p1 | e107_p1 | Module Setup | 2025/01/09 | 2025/02/01 | 24 | 24 | 1
e107 | 830D00010A | f39 | tool_p2 | Hardware Setup | p2 | e107_p2 | Hardware Setup | 2025/02/02 | 2025/03/02 | 29 | 29 | 1
e107 | 830D00010A | f39 | tool_p3 | Function Setup | p3 | e107_p3 | Function Setup | 2025/03/03 | 2025/03/15 | 13 | 21 | 1.6154
e107 | 830D00010A | f39 | tool_p4 | Utility | p4 | e107_p4 | Utility | 2025/03/16 | 2025/03/31 | 16 | 36 | 2.25
e108 | 840400019A | f40 | tool_p1 | Module Setup | p1 | e108_p1 | Module Setup | 2025/05/12 | 2025/05/12 | 1 | 3 | 3
e108 | 840400019A | f40 | tool_p2 | Hardware Setup | p2 | e108_p2 | Hardware Setup | 2025/05/13 | 2025/05/14 | 2 | 8 | 4
e108 | 840400019A | f40 | tool_p3 | Function Setup | p3 | e108_p3 | Function Setup | 2025/05/15 | 2025/05/15 | 1 | 5 | 5
e108 | 840400019A | f40 | tool_p4 | Utility | p4 | e108_p4 | Utility | 2025/05/16 | 2025/05/16 | 1 | 5 | 5
e109 | 840500001A | f6 | tool_p1 | Module Setup | p1 | e109_p1 | Module Setup | 2025/01/01 | 2025/01/27 | 27 | 129 | 4.7778
e109 | 840500001A | f6 | tool_p2 | Hardware Setup | p2 | e109_p2 | Hardware Setup | 2025/01/28 | 2025/03/01 | 33 | 154 | 4.6667
e109 | 840500001A | f6 | tool_p3 | Function Setup | p3 | e109_p3 | Function Setup | 2025/03/02 | 2025/03/26 | 25 | 51 | 2.04
e109 | 840500001A | f6 | tool_p4 | Utility | p4 | e109_p4 | Utility | 2025/03/27 | 2025/03/27 | 1 | 1 | 1
e110 | 840700002A | f41 | tool_p1 | Module Setup | p1 | e110_p1 | Module Setup | 2025/08/27 | 2025/10/06 | 41 | 115 | 2.8049
e110 | 840700002A | f41 | tool_p2 | Hardware Setup | p2 | e110_p2 | Hardware Setup | 2025/10/07 | 2025/11/19 | 44 | 249 | 5.6591
e110 | 840700002A | f41 | tool_p3 | Function Setup | p3 | e110_p3 | Function Setup | 2025/11/20 | 2025/12/22 | 33 | 157 | 4.7576
e110 | 840700002A | f41 | tool_p4 | Utility | p4 | e110_p4 | Utility | 2025/12/23 | 2026/01/23 | 32 | 66 | 2.0625